## Explanatory Note
Initiating the profiling exercise ¦ Workplan Explanatory Note
TOOL'S MAIN PURPOSE
This workplan template was developed by JIPS to support profiling partners in planning during the different phases of a profiling exercise. The workplan can be used together with the Budget tool to manage the profiling process. This document is typically developed in the initial phase of a profiling exercise. But it is a working document that should be revised periodically throughout the exercise. This workplan template aims to fulfill several OBJECTIVES: ✔ to provide a general overview of the essential outputs, activities and tasks of each of the six phases in a profiling exercise ✔ to provide the Profiling Working Group and/or Profiling Coordinator with a tool to realistically estimate the timeframes for the different activities in the profiling process ✔ to support the Profiling Working Group and/or Profiling Coordinator in keeping track of main tasks and duties during the profiling process This workplan tool does NOT aim: ✔ to provide an exhausting list of all steps in a profiling exercise. Given the context-specific characteristics of each profiling, the workplan should be adapted accordingly.
PROCESS FOR DEVELOPING AND ADAPTING THIS TOOL
Adapt activities and tasks to the context and the main objective of the profiling
Typically before a profiling is initiated, the scope of the exercise is defined in a Concept Note. In this phase it already makes sense to adapt the workplan where possible, for instance by reducing the amount of time needed for data collection if the objectives are very narrow in scope, and expanding it if the populations are very spread out or the exercise seeks to cover a large area. This helps partners understand the various activities in the process, get a realistic expectation of how long the process could take, and where specifically they would need to contribute resources.
Identify focal persons for specific activities
For each activity, a focal person could be identified to clarify the roles and responsibilities during the profiling. A Profiling Coordinator for instance may manage the process overall but would require that a Field Coordinator be hired to focus on the data collection phase, or that technical partners oversee the data processing and analysis. It may not be relevant to assign focal points from the outset but could be added later on as needed for coordination.
Adjust timeframes
Depending on the scope of the profiling and delays that may occur along the way, the time frames for each activity will vary. Hence, try to assess the time needed for each activity early on in the process, but update the workplan as changes occur to keep track of how changes will affect the overall timing. Two phases that are often overlooked in the planning are the time needed to invest in analysing the data after it has been collected, and the time needed to review, prepare and finalise a final profiling report. Making sure that these are included in the workplan reminds profiling partners to set aside resources for these phases.
Share with partners for review and feedback
This workplan can be printed (the template is currently formatted for A3 sized paper) and posted for others to review, or it can be shared as an attachment for the profiling partners to be clear about the activities and timeframes. This helps with transparency in the planning.

## Workplan Template
Workplan
Reminder: The overall timeframe and the individual tasks need to be adjusted for each exercise.
Phase | Key Outputs | Activities | Tasks | Focal person responsible | Prior | 6 - 8 months
[6 empty] | 1 | 2 | ? | 3 | ? | 4 | ? | 5 | ? | 6 | ? | 7 | ? | 8
Initiating a Profiling Exercise | Concept note and planning tools | Evaluate data needs | Outline data needs and cross-check them with existing secondary data.
|  | Outreach to stakeholders and discussions to initiate collaboration | Develop and implement a strategy to reach out to all stakeholders or potential partners, keeping in mind local partners.
Hold a meeting with stakeholders to come to a decision on whether to proceed with a profiling and to build consensus towards an overall objective for the exercise.
|  | Document decisions and plans with stakeholders | Organise a workshop to agree on the overall objective for the exercise.
Draft Concept Note, Budget and Workplan. Share with stakeholders for review and feedback.
Establishing a Collaborative Process | Structure for the Profiling Working Group | Organise meetings to engage stakeholders and to create a working group for joint decisions | Discuss and agree on organisational structure.
|  | Formalise the process | Jointly produce Terms of Reference with Working Group.
Draft memoranda of understanding with other partners if needed.
|  | Recruit a neutral Profiling Coordinator | Jointly develop Profiling Coordinator Terms of Reference.
Recruit a Profiling Coordinator.
Designing a Methodology | Comprehensive Methodology Document and Analysis Plan | Seek agreement on specific objectives and main components of the method | Organise meetings with partners to further develop objectives and expectations.
Agree on building blocks for methodology (target populations, geographic locations, topics, basic methods, etc).
Secondary Data Review and Population Mapping.
|  | Draft methodology & tools for data collection | Develop and seek agreement on an Analysis Plan outlining how the objectives translate to topics, indicators and then to data collection methods.
Develop and share Methodology Document for review and feedback from partners.
Draft data collection tools and share with partners
Draft Tabulation Plan for quantitative data and Coding Plan for qualitative data.
|  | Pilot of the tools for data collection | Perform a test of the tools by obtaining feedback from respondents.
Incorporate revisions.
Implementing Data Collection | Raw data from the field | Organizing logistics for field data collection | Select partners with data collection expertise and capacity.
Develop an operational plan to evaluate security risks and access constraints in the field.
Revise workplan and budget for data collection.
Recruit staff (interviewers, logistical and administrative assistance)
Prepare and implement awareness raising about profiling in target areas.
Acquire supplies, data collection materials and vehicles.
Prepare data collection tools (finalise mobile data collection application, print and copy questionnaires).
Draft field manuals and training materials.
|  | Capacity building of field staff | Conduct training workshops for enumerators, supervisors, team leaders, facilitators.
|  | Pilot in the field | Pilot data collection tools, mobile data collection application and processing in the field.
Update tools based on pilot and finalise staff training.
|  | Collect data in the field | Collect the data.
Daily monitoring of data collection and data storage.
Conclude data collection debrief with teams.
Processing and Analysing Data | Processed data and results of the analysis | Prepare for data processing | Form a technical working group with technical capacity.
Draft data processing and analysis strategy, clarifying roles & responsibilities and plan for documentation on changes to raw data.
|  | Analysis of quantitative data | Process and clean the data by identifying and correcting omissions and errors.
Analyse data following analysis plan with agreed-upon indicators and tabulation plan for preparing tables.
|  | Analysis of qualitative data | Translate and read transcripts and debrief with interviewers to ensure interpretability.
Analyse data following analysis plan with agreed-upon indicators and coding plan for organising and summarising categories.
|  | Collaborative data revision and consolidation of preliminary results | Consolidate preliminary findings into manageable format for presentation.
Prepare and conduct collaborative analysis workshop to receive feedback from partners.
Plan and conduct workshop with displaced communities to share results and discuss their perspective to obtain contextual information.
|  | Revision of results and next steps | Revise preliminary findings based on results from workshops and meetings and share as needed with partners for additional feedback.
Discuss next steps with Profiling Working Group to consolidate findings into dissemination materials and final report.
Validatiion, Reporting and Dissemination | Recommendations and dissemination materials, including final Profiling Report | Draft and validate final report | Draft final report with partners in the Profiling Working Group.
Share report with partners for review and feedback.
Plan validation workshop to endorse final results and jointly develop recommendations.
|  | Finalize report and and conduct dissemination | Finalise report with recommendations.
Send final report content to graphic designers and translators as needed.
Develop dissemination strategy for final report and other relevant dissemination efforts.
Distribute final report to various bodies (local and national government agencies, communities, UN agencies, local and international NGOs, etc.).
Conduct workshops with displaced communities to share results.
Prepare national or global-level workshop(s) to present the findings.
Upload final datasets to easy-to-access repositories (DART, HDX, etc.).